## Project Settings
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Javier Mesa
Start Date | abr 02, 2017 12:21:02 PM
Completion Date | abr 03, 2017 09:40:47 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:44 PM el 3/04/2017

## Overall Metrics
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 26.6 | 22.1 | 26.2
Planned Time | 0.17292 |  | 0.87778
Actual Tiempo |  | 0.19236 | 0.98125
CPI (Cost-Performance Index) |  |  | 0.89
% Reuse | 14.1% | 13.4% | 13.6%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 0 | 0 | 0
Total Defects/KLOC or equivalent | 27.2 | 0 | 22.7
Yield % | 71.4% | #DIV/0! | 71.4%
Code Review Rate | 616 | 306 | 537
% Appraisal COQ | 6.34% | 20.6% | 9.13%
% Failure COQ | 14.2% | 9.39% | 13.2%
COQ A/F Ratio | 0.45 | 2.19 | 0.69
PQI | 0.03 | 0.69 | 0.08
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:45 PM el 3/04/2017

## Program Size
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 242 | 242 | 611
Deleted (D) | 150 | 213 | 491
Modified (M) | 20 | 15 | 57
Added (A) | 90.3 | 87 | 560
Reused (R) | 30 | 18 | 107
Added and Modified (A+M) | 110 | 102 | 617
Total Size (T) | 212 | 134 | 787
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 108 | 102 | 507
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:45 PM el 3/04/2017

## Time In Phase
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.045139 | 0.038889 | 0.24514 | 25%
DiseÃ±o | 0.022917 | 0.043056 | 0.14722 | 15%
RevisiÃ³n de DiseÃ±o | 0.0034722 | 0.025694 | 0.041667 | 4.25%
CodificaciÃ³n | 0.059028 | 0.040278 | 0.30833 | 31.4%
RevisiÃ³n de CodificaciÃ³n | 0.0076389 | 0.013889 | 0.047917 | 4.88%
CompilaciÃ³n | 0.0125 | 0.011806 | 0.069444 | 7.08%
Pruebas | 0.011806 | 0.00625 | 0.060417 | 6.16%
Postmortem | 0.010417 | 0.0125 | 0.061111 | 6.23%
Total | 0.17292 | 0.19236 | 0.98125
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:46 PM el 3/04/2017

## Defects Injected
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.21 | 0 | 1 | 7.14%
DiseÃ±o | 1.5 | 0 | 7 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 1.29 | 0 | 6 | 42.9%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 3 | 0 | 14
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:46 PM el 3/04/2017

## Defects Removed
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.43 | 0 | 2 | 14.3%
CodificaciÃ³n | 1.5 | 0 | 7 | 50%
RevisiÃ³n de CodificaciÃ³n | 0.21 | 0 | 1 | 7.14%
CompilaciÃ³n | 0.86 | 0 | 4 | 28.6%
Pruebas | 0 | 0 | 0 | 0%
Total | 3 | 0 | 14
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:46 PM el 3/04/2017

## Defect Removal Efficiency
/Non Project/PSP Fundamentals & Advanced/Program 5
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 5.09 | 0 | 2
Defects/Hour - Code Review | 1.2 | 0 | 0.87
Defects/Hour - Compile | 2.82 | 0 | 2.4
Defects/Hour - Test | 0 | 0 | 0
DRL (DLDR/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Code Review/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Compile/UT) | #VALUE! | #DIV/0! | #DIV/0!
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:47 PM el 3/04/2017